## Project Planner
Eternal Inflation Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
Finish FV stuff | 1 | 3 | 1 | 0 | 20%
Incorporate FV | 3 | 1 | 0 | 0
Debug | 3 | 5 | 0 | 0
Initial runs | 4 | 3 | 0 | 0
Data analysis | 6 | 9 | 0 | 0
Full runs | 7 | 5 | 0 | 0
Package code | 14 | 2 | 0 | 0
Filler writing | 1 | 12 | 1 | 0 | 20%
Results writing | 9 | 6 | 0 | 0
Writing review | 12 | 4 | 0 | 0
Post to Arxiv | 15 | 1 | 0 | 0
Activity 11 | 0 | 0 | 0 | 0 | 60%
Activity 12 | 0 | 0 | 0 | 0 | 0%
Activity 13 | 0 | 0 | 0 | 0 | 50%
Activity 14 | 0 | 0 | 0 | 0 | 0%
Activity 15 | 0 | 0 | 0 | 0 | 1%
Activity 16 | 0 | 0 | 0 | 0 | 80%
Activity 17 | 0 | 0 | 0 | 0 | 0%
Activity 18 | 0 | 0 | 0 | 0 | 0%
Activity 19 | 0 | 0 | 0 | 0 | 0%
Activity 20 | 0 | 0 | 0 | 0 | 0%
Activity 21 | 0 | 0 | 0 | 0 | 44%
Activity 22 | 0 | 0 | 0 | 0 | 0%
Activity 23 | 0 | 0 | 0 | 0 | 12%
Activity 24 | 0 | 0 | 0 | 0 | 5%
Activity 25 | 0 | 0 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 50%

## Task List
Task | Assigned | Due |  | Review | Notes
Create task list and project planner spreadsheets | 2017-09-05 | 2017-09-05 | 1 | 2017-09-06
Test limiting gravity case | 2017-09-05 | 2017-09-05 | 1 | 2017-09-14 | Check limiting case of gravitational instanton (where there should be no gravitational effects).
Set up a git repository for eternal inflation code | 2017-09-05 | 2017-09-05 | 1 | 2017-09-06
Email STR notifying leave of absence | 2017-09-05 | 2017-09-06 | 0.5 | 2017-09-08
Follow-up with Cathy regarding TA availability | 2017-09-05 | 2017-09-06 | 1 | 2017-09-09 | Submit teaching preferences
Instanton write-up | 2017-09-05 | 2017-09-08 | 0.5 | 2017-09-14 | Write up existing work on instantons in style of hybrid inflation notes.
Instanton approximation | 2017-09-05 | 2017-09-12 | 0.25 | 2017-09-14 | Locate gravitational and non-gravitational approximations to instanton action.
Tunneling rate cutoff | 2017-09-05 | 2017-09-12 | 0 | 2017-09-14 | What is a sensible order-of-magnitude cutoff for tunneling rate given by approximations?
Give Anthony permissions for git repo | 2017-09-06 | 2017-09-14 | 0 | 2017-09-14
Enroll in Independent Study and Seminars | 2017-09-05 | 2017-09-14 | 1 | 2017-09-14 | Cosmology (just talks) or something else? (Particle Physics?)
Write up description of false vacuum procedure | 2017-09-06 | 2017-09-14 | 0.25 | 2017-09-14
Check thresholds & units for all quantities in code | 2017-09-05 | 2017-09-21 | 0 | 2017-09-21
Finalize output structure from simulation | 2017-09-06 | 2017-09-21 | 0.5 | 2017-09-21 | Which quantities should I record from the simulation? How should I record them?
Enforce parameters | 2017-09-08 | 2017-09-21 | 0 | 2017-09-21
Write scripts to run simulation | 2017-09-06 | 2017-09-25 | 0.25 | 2017-09-28
Gather to-date references for paper | 2017-09-05 | 2017-09-28 | 0.5 | 2017-09-28 | Get proper references for code borrowed from Max Tegmark, Max Wainwright
Populate "Code" appendix | 2017-09-08 | 2017-11-21 | 0.25 | 2017-11-21 | Create an appendix to describe workings of the code in detail