## Sheet1
Task | Assigned | Due |  | Review | Notes
Create task list and project planner spreadsheets | 2017-09-05 | 2017-09-05 | 1 | 2017-09-06
Email STR notifying leave of absence | 2017-09-05 | 2017-09-06 | 0.5 | 2017-09-08
Follow-up with Cathy regarding TA availability | 2017-09-05 | 2017-09-06 | 0 | 2017-09-08
Test limiting gravity case | 2017-09-05 | 2017-09-05 | 1 | 2017-09-14 | Check limiting case of gravitational instanton (where there should be no gravitational effects).
Set up a git repository for eternal inflation code | 2017-09-05 | 2017-09-05 | 1 | 2017-09-14
Instanton approximation | 2017-09-05 | 2017-09-08 | 0.2 | 2017-09-14 | Locate grav and non-grav approximations to instanton action.
Tunneling rate cutoff | 2017-09-05 | 2017-09-12 | 0 | 2017-09-14 | What is a sensible order-of-magnitude cutoff for tunneling rate given by approximations?
Instanton write-up | 2017-09-05 | 2017-09-14 | 0.2 | 2017-09-14 | Write up existing work on instantons in style of hybrid inflation notes.
Enroll in Independent Study and Seminars | 2017-09-05 | 2017-09-14 | 0 | 2017-09-14 | Cosmology (just talks) or something else? (Particle Physics?)
Check thresholds & units for all quantities in code | 2017-09-05 | 2017-09-21 | 0 | 2017-09-21
Gather to-date references for paper | 2017-09-05 | 2017-09-28 | 0.2 | 2017-09-28